Pamoja+

3-Month Launch Timeline

A realistic, low-burden execution plan

Focused goals. Clean execution. Measured growth. Dar es Salaam only for Q1.

Version 2 — Clean rewrite with audit corrections applied

Grow Together. Shop Smarter.

# 1. Overall 3-Month Goal

The first three months focus on building a clean operating rhythm in Dar es Salaam rather than launching everything at once. Pamoja+ proves that businesses will join, shoppers will engage, and selected sellers will pay for visibility.

Q1 scope: Dar es Salaam only (Kinondoni, Ilala, Ubungo). No outreach to Mwanza, Arusha, or Dodoma until the Month 4 review.

| Area | 3-Month Target |
| --- | --- |
| Businesses onboarded | 40–60 |
| Active sellers | 25–35 |
| Product / deal listings | 150+ |
| Paid sellers or paid promotions | 5–15 |
| Active ambassadors | 10 |
| Posting rhythm | 4–6 quality posts per week |
| First revenue target (cumulative across 3 months) | TZS 300,000 – 1,500,000 |

# 2. Content language

Captions and shopper-facing content are Swahili-first. English is used as a secondary language for diaspora customers and corporate partners.

# 3. Month 1 — Foundation and Soft Setup

Prepare the structure, seller process, marketplace categories, communication flow, and first group of sellers. The objective is controlled learning, not mass expansion.

| Week | Focus | Key Actions | Target Output |
| --- | --- | --- | --- |
| Week 1 | Internal setup | Finalize profile, pricing, team roles, seller form, listing template, support line, launch categories. | Core documents and workflows ready. |
| Week 2 | Seller preparation | List 50 potential businesses, prepare pitch messages, contact first 10. | Lead list and onboarding tracker ready. |
| Week 3 | First onboarding | Onboard 10–15 sellers, collect photos/details, publish first listings, test inquiry flow. | 10–15 sellers, 30–50 listings live. |
| Week 4 | Soft launch | Announce Pamoja+, post deal highlights, share business spotlights, collect feedback. | 15–20 sellers, 50+ listings live. |

## Starting categories

- Food and beverages.

- Wellness and health lifestyle (educational content only).

- Beauty and personal care.

- Fashion and accessories.

- Home essentials.

- Services and local deals.

# 4. Month 2 — Market Testing and Community Growth

Grow carefully while testing what customers and sellers actually respond to. Learn which categories, posts, deals, and businesses are most promising.

| Week | Focus | Key Actions | Target Output |
| --- | --- | --- | --- |
| Week 5 | Improve listings | Review profiles, improve weak descriptions, organize categories, prepare content calendar. | Cleaner marketplace presentation. |
| Week 6 | Grow sellers | Contact 20–30 more businesses, onboard 10–15, focus on best-performing categories. | 25–35 total sellers. |
| Week 7 | Ambassador pilot | Recruit 5–10 ambassadors per the Ambassador Verification SOP. Set referral targets, track and reward. | Ambassador system tested. |
| Week 8 | Performance review | Review top sellers, top categories, best posts, complaints, paid promotion interest. | Clear focus for Month 3. |

## Paid promotion test (aligned with Payment Structure v2)

- Daily Deal Boost: TZS 5,000 per day.

- Weekly Deal Boost: TZS 25,000 per week.

- Featured Brand Slot: TZS 50,000 per week.

- Only pitch paid visibility to sellers who are already active and responsive.

# 5. Month 3 — Stabilization and Light Monetization

Turn the early test into a repeatable operating model. Focus on seller retention, trust, paid visibility, basic partnerships, and a clear next-quarter plan.

| Week | Focus | Key Actions | Target Output |
| --- | --- | --- | --- |
| Week 9 | Paid packages | Introduce Free Plan, TZS 15,000 Growth, TZS 35,000 Plus, and TZS 75,000 Partner to active sellers. | First upgrades and proper revenue tracking. |
| Week 10 | Customer trust | Verified seller badges, responsive seller labels, testimonials, expired-deal cleanup, complaint flow. | Stronger trust system. |
| Week 11 | Partnership push | Pitch 5 high-potential brands, target 1–2 Brand Spotlight campaigns (TZS 100,000–200,000). | 1–2 campaigns secured or in discussion. |
| Week 12 | Review and plan | Review revenue, sellers, weak categories, workload, feedback. Prepare Month 4–6 plan. | Next-quarter plan based on real data. |

# 6. Weekly Operating Rhythm

| Day | Focus | Main Actions |
| --- | --- | --- |
| Monday | Planning | Review last week, set goals, confirm onboardings and deals, assign tasks. |
| Tue–Thu | Execution | Contact sellers, upload listings, create content, promote deals, respond to inquiries. |
| Friday | Review | Update database, remove expired deals, check payments, review results, prepare next week. |
| Weekend | Light activity | One deal or community update; urgent messages only. |

# 7. Minimum Team

- Lead / Founder — direction, approvals, partnerships.

- Operations Person — listings, deals, workflow.

- Business Development — outreach and onboarding.

- Marketing / Content — social media, deals, brand stories.

- Tech Support — platform updates and analytics.

- Finance / Admin — payment records and reporting.

- Ambassadors — referrals and community sharing.

# 8. What Not to Do in the First 3 Months

- Do not build a complicated app before testing demand.

- Do not hire a large team too early.

- Do not create too many categories at once.

- Do not manage delivery in-house at the beginning.

- Do not force every seller to pay immediately.

- Do not launch complex rewards before the basic marketplace works.

- Do not run too many campaigns at once.

- Do not expand outside Dar es Salaam in Q1.

- Do not host TMDA-regulated wellness claims.

# 9. End-of-Quarter Review

- Which businesses received the most inquiries?

- Which categories performed best?

- Which sellers are willing to pay?

- Which promotions generated real engagement?

- What confused customers?

- What took too much team time?

- What should be stopped, repeated, or improved?

Final note: The goal is not perfection. The goal is a clean, trusted, repeatable marketplace process that can grow month by month.